## IA Timeline (No DPB Approval)
MARYLAND DEPARTMENT OF HEALTH
PREVENTION AND HEALTH PROMOTION ADMINISTRATION
PRELIMINARY IA TIMELINE (No DBM Approval Required)
Instructions:
Please note this sheet is protected in order to maintain the formulas incorporated in these calculations.
Step 1 - Cell D34 (Green) Please enter the Anticipated Start Date. If your contract requires a startup period, please include that time in this date.
Step 2 - Please enter actual dates in Column E, once they occur.
Actions that require completion by the Program are in Bold.
Actions that require completion by OPASS are in Italics.
Items in Red are items relating to deadlines included in the IA.
STEP | DAYS | Estimated Date | Actual Date | Comments
Send IA Report and Checklist to OPASS | 14 | 2018-04-06
OPASS will notify when checklist is approved | 14 | 2018-04-20
Once approved by OPASS, Final IA Packet to OPASS (hard copies and 3 signed IA's) | 14 | 2018-05-04
ADPICS approval | 7 | 2018-05-18
OPASS Award | 5 | 2018-05-25
Forward IA To Appropriate Deputy Secretary For Approval | 14 | 2018-06-01
Forward Signed IA's To Program | 14 | 2018-06-15
IA Start Date |  | 2018-07-01
Formulas:
Estimated Date = IF(WEEKDAY([Estimated Date, row below]-[DAYS],1)=7,[Estimated Date, row below]-[DAYS]-2,+IF(WEEKDAY([Estimated Date, row below]-[DAYS],1)=1,[Estimated Date, row below]-[DAYS]-2,[Estimated Date, row below]-[DAYS]+0))

## IA Timeline (DPB Approval)
MARYLAND DEPARTMENT OF HEALTH
PREVENTION AND HEALTH PROMOTION ADMINISTRATION
PRELIMINARY IA TIMELINE (DBM Approval Required)
Instructions:
Please note this sheet is protected in order to maintain the formulas incorporated in these calculations.
Step 1 - Cell D34 (Green) Please enter the Anticipated Start Date. If your contract requires a startup period, please include that time in this date.
Step 2 - Please enter actual dates in Column E, once they occur.
Actions that require completion by the Program are in Bold.
Actions that require completion by OPASS are in Italics.
Items in Red are items relating to deadlines included in the IA.
STEP | DAYS | Estimated Date | Actual Date | Comments
Send IA Report and Checklist to OPASS | 14 | 2018-02-16
Submit Completed IA Packet to Lauren in Word form via email | 14 | 2018-03-02
OPASS will send information to DBM for review | 5 | 2018-03-16
DBM approval, may require discussions via email or conference call | 40 | 2018-03-23
Once approved by DBM, Final IA Packet to OPASS (hard copies and 3 signed IA's) | 14 | 2018-05-04
ADPICS approval | 7 | 2018-05-18
OPASS Award | 5 | 2018-05-25
Forward IA To Appropriate Deputy Secretary For Approval | 14 | 2018-06-01
Forward Signed IA's To Program | 14 | 2018-06-15
IA Start Date |  | 2018-07-01
Formulas:
Estimated Date = IF(WEEKDAY([Estimated Date, row below]-[DAYS],1)=7,[Estimated Date, row below]-[DAYS]-2,+IF(WEEKDAY([Estimated Date, row below]-[DAYS],1)=1,[Estimated Date, row below]-[DAYS]-2,[Estimated Date, row below]-[DAYS]+0))

## IA Documentation Checklist
IA Process (No DBM Approval) | IA Process (DBM Approval) over $500,000
OPASS forms can be found at : | OPASS forms can be found at :
https://health.maryland.gov/Pages/sf_dcpf.aspx | https://health.maryland.gov/Pages/sf_dcpf.aspx
New IA | New IA
Documentation Submitted to Lauren (Hard Copies) | Documentation Submitted to Lauren (Word Versions)
1. IA Report-IAAR | 1. IA Report-IAAR
2. IA Checklist | 2. IA Checklist
3. Fund Cert | 3. Fund Cert
5. IA Cover Sheet | 4. Attachment 1
6. IA Template | 5. IA Cover Sheet
7. Attachment A - Scope of Work | 6. Attachment A - Scope of Work
8. Attachmment B- Detailed Budget | 7. Attachment B - Detailed Budget
8. 2 Example Invoices (PDF)
9. IA Template
IA Option
IA Option
Documentation Submitted to Lauren (Hard Copies)
1. IA Report-IAAR | Documentation Submitted to Lauren (Word Versions)
2. IA-Opt-Cover-Sheet | 1. IA Report-IAAR
3. Fund Cert | 2. IA-Opt-Cover-Sheet
4. IA Option Template | 3. Fund Cert
5. Attachment A - Scope of Work | 4. Attachment 2
6. Attachment B - Revised Budget | 5. IA Option Template
6. Attachment A - Scope of Work
7. Attachment B - Revised Budget
IA Modification
IA Modification
Documentation Submitted to Lauren (Hard Copies)
1. IA Report-IAAR | Documentation Submitted to Lauren (Word Versions)
2. IA-MOD-Cover-Sheet | 1. IA Report-IAAR
3. Fund Cert | 2. IA-MOD-Cover-Sheet
4. IA MOD Template | 3. Fund Cert
5. Attachment A - Scope of Work | 4. Attachment 2
6. Attachment B - Revised Budget | 5. IA MOD Template
6. Attachment A - Scope of Work
7. Attachment B - Revised Budget