## Slide 1: Prince George’s County Health Department
UPDATES FROM THE PGCHEZ
Pamela Creekmur, Health Officer

## Slide 2: Year One Core Goals of the Zone
Key Milestones | Year One |  |  | 
 | Q1 | Q2 | Q3 | Q4
Goal 1: Increase access to primary care services |  |  |  | 
Open and/or expand 2 new PCMH sites in the Zone |  |  |  | 
Develop and Initiate Community Health Worker program |  |  |  | 
Goal 2: Increase community health resources |  |  |  | 
Develop a Health Information Exchange (HIE) and connect various electronic medical records to the HIE |  |  |  | 
Develop and implement care coordination software application |  |  |  | 
Establish post discharge care coordination protocols |  |  |  | 
Develop and implement electronic Healthy Eating Active Living Wellness Plan Template |  |  |  | 
Conduct health literacy surveys |  |  |  | 
Goal 3: Promote Cultural Competency |  |  |  | 
Develop comprehensive cultural competency training curriculum |  |  |  | 
 | Completed |  | On-Task |  | Delayed
Notes: KEY MILESTONES
Goal 1: Increase access to primary care services
Completed Global Vision opening and on task at Q4 with Greater Baden Medical Services expansion in Zone
Completed the development and initiated the community health worker program
Goal 2: Increase community health resources
Completed development of the health information exchange (HIE) and connection to the State HIE, but delayed in the connectivity to the various PCMHs and hospital electronic medical records to the HIE
On task with development and completion of the needs requirement documents for the Care Coordination software application, but delayed in acquiring the software.
On task establishing post discharge care coordination protocols
On task developing and delayed in implementation of electronic Healthy Eating Active Living Wellness Plan Template
On task developing and conducting health literacy surveys
Goal 3: Promote Cultural Competency
Comprehensive cultural competency curriculum developed and on task as of Q3
State will provide training to providers in year 2
Completed Milestones in Year 1
Opened and staff at Global Vision PCMH site
Expanded services at Greater Baden PCMH site
Identified additional service provided by Prince George’s County Heath Department (complementing PCMH-related services in the Zone

## Slide 3: Process Measures
Process Measures | Year One Goals | Year One Cumulative Totals |  |  | 
 |  | Q1 | Q2 | Q3 | Q4
# of HEZ practitioners added* (FTE) | 7 | 0 | 0 | 2.5 | 8.3
# of CHWs added (FTE) | 5 | 0 | 0 | 3.0 | 5.0
# of patients (unduplicated) across Zone |  | Opened Q4 |  |  | 925
# of patient visits across Zone |  |  |  |  | 3,251
# of CHW outreach encounters |  |  |  |  | 6,000
Notes: YEAR ONE CORE GOALS OF THE ZONE
Increase the primary care workforce
Added 8.3 HEZ practitioners by end of Q4
  Added 6.8 physicians, PA, and NPs category
  Added 1.5 clinical nurses category
Added 5 community health workers by end of Q4
At Q4 925 unduplicated patients seen across Zone
At Q4 3,251 patient visits across the Zone
At Q4 community health workers conducted over 6,000 outreach encounters assisting Zone residents

## Slide 4: Challenges & Overcoming Barriers in the Zone
Challenge | State Assistance Needed
Identifying suitable properties to serve as healthcare facilities | Funding sources, property renovation, and contractor management
Establishing the interfaces between HIE and the Zone providers’ electronic health record (EMR) system | Need additional funds from state for interfaces
Developing a complete measure of hospital inpatient admissions and readmissions for the HEZ | Obtaining Maryland data from CRISP and pursuing DC data
Lack of marketing funds and start-up operating capital | Need additional funds from state
Notes: Identifying suitable properties to serve as healthcare facilities
Enlisted assistance of County agencies for funding sources, property renovation, and contractor management
Establishing the interface between HIE and the Zone providers’ electronic health record (EMR) system
PGCHEZ submitted proposal to private foundation to work to secure adding funding to support this task
Need additional funds from state for interface
Developing a complete measure of hospital inpatient admissions and readmissions for the HEZ
Enlisted technical assistance provided by the State for readmission data available through CRISP
Hiring Delays and Other Challenges
CHW recruitment delays due to time required to secure approvals for contracts, agreements, and consents
Limited health literacy of some community residents
Difficulty recruiting residents in Zone to switch care to Zone providers instead of outside of the Zone
Manpower and hours required for community canvasing to keep residents informed
Lack of Marketing Funds
New PCMHs did not have sufficient funds to support the marketing and outreach to attract new patients
New PCMHs did not have sufficient operating capital
Health Department has leveraged other projects to assist HEZ and developed communications and website development as part of Be a Part of the Healthy Revolution

## Slide 5: Update on Year 2 Core Strategic Goals
Strategic Goals | Status
Increase accessibility and availability of primary care services in 20743 | Complete build out project for Gerald Family Care PCMH by Fall Year 2 Secure addition support for PGCHEZ operating costs and prepare proposal applications Establish two PCMHs hubs in Year 2-One on task and the other is pending agreements finalized for Dimensions Provider PCMH
Improve health outcomes for the residents of zip code 20743 | Delayed to August and October 2014
Increase the number of community health workers delivering services | Completed
Notes: UPDATE ON YEAR 2 CORE STRATEGIC GOALS
Goal 1: Increase accessibility and availability of primary care services in 20743
  Complete build out project for Gerald Family Care PCMH by Fall Year 2-on task
  Secure addition support for PGCHEZ operating costs and prepare proposal applications-on task
  Establish two PCMHs hubs in Year 2-One on task and the other is pending agreements finalized for Dimensions Provider PCMH-on task
Goal 2: Improve health outcomes for the residents of zip code 20743
  Delayed to August and October 2014
Goal 3: Increase the number of community health workers delivering services
  Completed
Goal 4: Increase community resources for health
  Delays due to care coordination software implementation
Goal 5: Reduce preventable hospitalizations and emergency department (ED) visits
  Wellness plans created and TA for providers and training delayed until September, 2014
Goal 6: Monitor and evaluate PGCHEZ process and outcomes
  Completed data collection tools and other objective delayed pending IRB approvals

## Slide 6: Update on Year 2 Core Strategic Goals
Strategic Goals | Status
Increase community resources for health | Delays due to Care Coordination software implementation
Reduce preventable hospitalizations and emergency department (ED) visits | Wellness plans created and TA for providers and training delayed until September, 2014
Monitor and evaluate PGCHEZ process and outcomes | Completed data collection tools and other objective delayed pending IRB approvals
Added Value | Consent 2 Share  Health Department awarded a six-month pilot project funded by SAMHSA contract in the amount of $340K

## Slide 7: Year One Modification and Unexpended Funds
Prior request submitted to carry over $79K (this was approved by the Commission at the last meeting/January 2014)
  Care Coordination Software development costs $50K
    Delayed at Q4 due to contract not fully executed.
    Status: Contract fully executed; funds expended
  Health Data Web Portal development costs $29K
    Delayed at Q4 due to contract not fully executed
    Status: Contract fully executed; funds expended
All other project funds expended to date in the amount of $1,035,854 (Tax and hiring credits not included in amount.)

## Slide 8: Questions