## IFB Timeline
MARYLAND DEPARTMENT OF HEALTH
OFFICE OF PROCUREMENT AND SUPPORT SERVICES
PRELIMINARY IFB TIMELINE
STEP | DAYS | DATE
Require Decision to Program | 295 | 2018-05-14
CFT | 100 | 2019-03-04
PRG | 30 | 2019-06-10
DBM/DoIT REVIEW | 40 | 2019-07-10
eMM POSTING | 14 | 2019-08-19
PRE-BID DATE | 14 | 2019-09-02
Q & A CUT OFF | 7 | 2019-09-16
BIDS DUE (21 days afer posting on eMM) | 21 | 2019-09-23
MBE INFORMATION CHECKED | 1 | 2019-10-14
RECOMMENDATION LETTER FORWARDED TO OPASS (info and references checked) | 7 | 2019-10-15
LETTERS TO VENDORS - RECOMMENDED VENDOR AND LOSING VENDORS | 7 | 2019-10-22
CONTRACT REVIEW (to ensure all information is received and vetted) | 7 | 2019-10-29
ENTER CONTRACT INFORMATION INTO ADPICS | 1 | 2019-11-05
SUBMIT CONTRACT FOR LEGAL APPROVAL | 1 | 2019-11-06
SUBMIT BPW ACTION AGENDA (along with misc paperwork) all two board meetings | 34 | 2019-11-07
FINALIZE INFORMATION IN ADPICS | 7 | 2019-12-11
FORWARD CONTRACT TO APPROPRIATE DEPUTY SECRETARY FOR APPROVAL | 7 | 2019-12-18
FORWARD SIGNED CONTRACTS TO PROGRAM | 7 | 2019-12-25
CONTRACT START DATE | 14 | 2020-01-01
* Populate Row 25, Column 'C' using numerical format (e.g., 1/1/19) to calculate start date for drafting the documents.
Formulas:
DATE = IF(WEEKDAY([DATE, row below]-[DAYS],1)=7,[DATE, row below]-[DAYS]+2,+IF(WEEKDAY([DATE, row below]-[DAYS],1)=1,[DATE, row below]-[DAYS]+1,[DATE, row below]-[DAYS]+0))